## Project_Management
Task ID | Task Description | Project Name | Assigned To | Start Date | Due Date | Status
TSK001 | Define Project Scope | Website Redesign | Alice | 2025-03-01 | 2025-03-15 | Completed
TSK002 | Create Wireframes | Website Redesign | Bob | 2025-03-16 | 2025-03-30 | Completed
TSK003 | Design Mockups | Website Redesign | Alice | 2025-04-01 | 2025-04-15 | In Progress
TSK004 | Develop Homepage | Website Redesign | Charlie | 2025-04-16 | 2025-04-30 | Not Started
TSK005 | Plan Marketing Campaign | Q2 Marketing | Diana | 2025-03-10 | 2025-03-25 | Completed
TSK006 | Create Social Media Content | Q2 Marketing | Evan | 2025-03-26 | 2025-04-10 | Completed
TSK007 | Launch Email Blast | Q2 Marketing | Diana | 2025-04-11 | 2025-04-18 | In Progress
TSK008 | Setup Ad Spend | Q2 Marketing | Fiona | 2025-04-19 | 2025-04-25 | Not Started
TSK009 | Research Competitors | Product Launch | George | 2025-04-01 | 2025-04-10 | Completed
TSK010 | Finalize Product Specs | Product Launch | Hannah | 2025-04-11 | 2025-04-20 | Not Started
TSK011 | User Testing Phase 1 | Product Launch | Ian | 2025-04-21 | 2025-05-05 | Not Started
TSK012 | Prepare Onboarding Docs | HR System Update | Julia | 2025-03-15 | 2025-04-05 | Completed
TSK013 | Train HR Staff | HR System Update | George | 2025-04-06 | 2025-04-15 | In Progress
TSK014 | System Go-Live Notification | HR System Update | Julia | 2025-04-16 | 2025-04-20 | Not Started
TSK015 | Write Blog Post | Content Creation | Kevin | 2025-03-20 | 2025-04-05 | Completed
TSK016 | Design Infographic | Content Creation | Laura | 2025-04-06 | 2025-04-22 | In Progress
TSK017 | Review Article | Content Creation | Michael | 2025-04-23 | 2025-05-07 | Not Started
TSK018 | Update Project Plan | Project Alpha | Nancy | 2025-03-01 | 2025-03-10 | Completed
TSK019 | Hold Kick-off Meeting | Project Alpha | Oliver | 2025-03-11 | 2025-03-18 | Completed
TSK020 | Gather Requirements | Project Alpha | Patricia | 2025-03-19 | 2025-04-02 | Completed
TSK021 | Develop Prototype | Project Beta | Quinn | 2025-03-25 | 2025-04-12 | Completed
TSK022 | Get Feedback on Prototype | Project Beta | Rachel | 2025-04-13 | 2025-04-25 | In Progress
TSK023 | Iterate on Design | Project Beta | Samuel | 2025-04-26 | 2025-05-10 | Not Started
TSK024 | Create User Stories | Software Dev | Theresa | 2025-04-01 | 2025-04-18 | In Progress
TSK025 | Develop Backend | Software Dev | Victor | 2025-04-19 | 2025-05-03 | Not Started
TSK026 | Test API | Software Dev | Wendy | 2025-05-04 | 2025-05-15 | Not Started
TSK027 | Prepare Training Materials | New Employee Onboarding | Xavier | 2025-03-10 | 2025-03-25 | Completed
TSK028 | Conduct First Day Orientation | New Employee Onboarding | Yvonne | 2025-03-26 | 2025-04-05 | Completed
TSK029 | Assign Buddy | New Employee Onboarding | Zachary | 2025-04-06 | 2025-04-16 | In Progress
TSK030 | Follow-up Meeting | New Employee Onboarding | Bella | 2025-04-17 | 2025-04-24 | Not Started
TSK031 | Finalize Budget | Budget Planning | Caleb | 2025-03-01 | 2025-03-10 | Completed
TSK032 | Present to Stakeholders | Budget Planning | Daisy | 2025-03-11 | 2025-03-20 | Completed
TSK033 | Get Approval | Budget Planning | Ethan | 2025-03-21 | 2025-04-01 | Completed
TSK034 | Implement Budget | Budget Planning | Faith | 2025-04-02 | 2025-04-15 | Completed
TSK035 | Monitor Expenses | Budget Planning | Caleb | 2025-04-16 | 2025-05-01 | Not Started
TSK036 | Gather Customer Feedback | Product Improvement | Daisy | 2025-04-01 | 2025-04-12 | Completed
TSK037 | Analyze Feedback | Product Improvement | Ethan | 2025-04-13 | 2025-04-20 | In Progress
TSK038 | Propose Improvements | Product Improvement | Faith | 2025-04-21 | 2025-05-05 | Not Started
TSK039 | Document Requirements | New Feature Dev | George | 2025-04-08 | 2025-04-22 | In Progress
TSK040 | Design UI/UX | New Feature Dev | Hannah | 2025-04-23 | 2025-05-07 | Not Started
TSK041 | Develop Feature | New Feature Dev | Ian | 2025-05-08 | 2025-05-22 | Not Started
TSK042 | Create Test Cases | Quality Assurance | Julia | 2025-04-15 | 2025-04-29 | In Progress
TSK043 | Execute Tests | Quality Assurance | Kevin | 2025-04-30 | 2025-05-14 | Not Started
TSK044 | Report Bugs | Quality Assurance | Laura | 2025-05-15 | 2025-05-29 | Not Started
TSK045 | Update Documentation | Knowledge Base | Michael | 2025-04-01 | 2025-04-18 | In Progress
TSK046 | Review Articles | Knowledge Base | Nancy | 2025-04-19 | 2025-05-03 | Not Started
TSK047 | Publish Updates | Knowledge Base | Oliver | 2025-05-04 | 2025-05-18 | Not Started
TSK048 | Plan Next Sprint | Agile Development | Patricia | 2025-04-14 | 2025-04-17 | Completed
TSK049 | Conduct Daily Stand-up | Agile Development | Quinn | 2025-04-18 | 2025-04-25 | In Progress
TSK050 | Hold Sprint Review | Agile Development | Rachel | 2025-04-26 | 2025-04-29 | Not Started

## Pivot Table
Count of Task ID | Column Labels
Row Labels | Completed | In Progress | Not Started | Grand Total
Agile Development | 1 | 1 | 1 | 3
Budget Planning | 2 | 2 | 1 | 5
Content Creation | 1 | 1 | 1 | 3
HR System Update | 1 | 1 | 1 | 3
Knowledge Base |  | 1 | 2 | 3
New Employee Onboarding | 1 | 2 | 1 | 4
New Feature Dev |  | 1 | 2 | 3
Product Improvement | 1 | 1 | 1 | 3
Product Launch |  | 2 | 1 | 3
Project Alpha | 2 | 1 |  | 3
Project Beta |  | 2 | 1 | 3
Q2 Marketing | 3 | 1 |  | 4
Quality Assurance |  | 1 | 2 | 3
Software Dev |  | 1 | 2 | 3
Website Redesign | 1 | 2 | 1 | 4
Grand Total | 13 | 20 | 17 | 50

## Dashboard
Project Dashboard
Count of Task ID | Column Labels
Row Labels | Completed | In Progress | Not Started | Grand Total
Agile Development | 1 | 1 | 1 | 3
Budget Planning | 2 | 2 | 1 | 5
Content Creation | 1 | 1 | 1 | 3
HR System Update | 1 | 1 | 1 | 3
Knowledge Base |  | 1 | 2 | 3
New Employee Onboarding | 1 | 2 | 1 | 4
New Feature Dev |  | 1 | 2 | 3
Product Improvement | 1 | 1 | 1 | 3
Product Launch |  | 2 | 1 | 3
Project Alpha | 2 | 1 |  | 3
Project Beta |  | 2 | 1 | 3
Q2 Marketing | 3 | 1 |  | 4
Quality Assurance |  | 1 | 2 | 3
Software Dev |  | 1 | 2 | 3
Website Redesign | 1 | 2 | 1 | 4
Grand Total | 13 | 20 | 17 | 50

## Working Sheet
Task ID | Task Description | Project Name | Assigned To | Start Date | Due Date | Status | Is Overdue?
TSK001 | Define Project Scope | Website Redesign | Alice | 2025-03-01 | 2025-03-15 | In Progress | Yes
TSK002 | Create Wireframes | Website Redesign | Bob | 2025-03-16 | 2025-03-30 | Completed | No
TSK003 | Design Mockups | Website Redesign | Alice | 2025-04-01 | 2025-04-15 | In Progress | No
TSK004 | Develop Homepage | Website Redesign | Charlie | 2025-04-16 | 2025-04-30 | Not Started | No
TSK005 | Plan Marketing Campaign | Q2 Marketing | Diana | 2025-03-10 | 2025-03-25 | Completed | No
TSK006 | Create Social Media Content | Q2 Marketing | Evan | 2025-03-26 | 2025-04-10 | Completed | No
TSK007 | Launch Email Blast | Q2 Marketing | Diana | 2025-04-11 | 2025-04-18 | In Progress | No
TSK008 | Setup Ad Spend | Q2 Marketing | Fiona | 2025-04-19 | 2025-04-25 | Completed | No
TSK009 | Research Competitors | Product Launch | George | 2025-04-01 | 2025-04-10 | In Progress | Yes
TSK010 | Finalize Product Specs | Product Launch | Hannah | 2025-04-11 | 2025-04-20 | In Progress | No
TSK011 | User Testing Phase 1 | Product Launch | Ian | 2025-04-21 | 2025-04-05 | Not Started | Yes
TSK012 | Prepare Onboarding Docs | HR System Update | Julia | 2025-03-15 | 2025-04-05 | Completed | No
TSK013 | Train HR Staff | HR System Update | George | 2025-04-06 | 2025-04-15 | In Progress | No
TSK014 | System Go-Live Notification | HR System Update | Julia | 2025-04-16 | 2025-04-20 | Not Started | No
TSK015 | Write Blog Post | Content Creation | Kevin | 2025-03-20 | 2025-04-05 | Completed | No
TSK016 | Design Infographic | Content Creation | Laura | 2025-04-06 | 2025-04-22 | In Progress | No
TSK017 | Review Article | Content Creation | Michael | 2025-04-23 | 2025-05-07 | Not Started | No
TSK018 | Update Project Plan | Project Alpha | Nancy | 2025-03-01 | 2025-03-10 | Completed | No
TSK019 | Hold Kick-off Meeting | Project Alpha | Oliver | 2025-03-11 | 2025-03-18 | In Progress | Yes
TSK020 | Gather Requirements | Project Alpha | Patricia | 2025-03-19 | 2025-04-02 | Completed | No
TSK021 | Develop Prototype | Project Beta | Quinn | 2025-03-25 | 2025-04-12 | In Progress | Yes
TSK022 | Get Feedback on Prototype | Project Beta | Rachel | 2025-04-13 | 2025-04-25 | In Progress | No
TSK023 | Iterate on Design | Project Beta | Samuel | 2025-04-26 | 2025-05-10 | Not Started | No
TSK024 | Create User Stories | Software Dev | Theresa | 2025-04-01 | 2025-04-18 | In Progress | No
TSK025 | Develop Backend | Software Dev | Victor | 2025-04-19 | 2025-05-03 | Not Started | No
TSK026 | Test API | Software Dev | Wendy | 2025-05-04 | 2025-05-15 | Not Started | No
TSK027 | Prepare Training Materials | New Employee Onboarding | Xavier | 2025-03-10 | 2025-03-25 | Completed | No
TSK028 | Conduct First Day Orientation | New Employee Onboarding | Yvonne | 2025-03-26 | 2025-04-05 | In Progress | Yes
TSK029 | Assign Buddy | New Employee Onboarding | Zachary | 2025-04-06 | 2025-04-12 | In Progress | Yes
TSK030 | Follow-up Meeting | New Employee Onboarding | Bella | 2025-04-17 | 2025-04-24 | Not Started | No
TSK031 | Finalize Budget | Budget Planning | Caleb | 2025-03-01 | 2025-03-10 | In Progress | Yes
TSK032 | Present to Stakeholders | Budget Planning | Daisy | 2025-03-11 | 2025-03-20 | Completed | No
TSK033 | Get Approval | Budget Planning | Ethan | 2025-03-21 | 2025-04-01 | In Progress | Yes
TSK034 | Implement Budget | Budget Planning | Faith | 2025-04-02 | 2025-04-12 | Completed | No
TSK035 | Monitor Expenses | Budget Planning | Caleb | 2025-04-16 | 2025-05-01 | Not Started | No
TSK036 | Gather Customer Feedback | Product Improvement | Daisy | 2025-04-01 | 2025-04-12 | Completed | No
TSK037 | Analyze Feedback | Product Improvement | Ethan | 2025-04-13 | 2025-04-20 | In Progress | No
TSK038 | Propose Improvements | Product Improvement | Faith | 2025-04-21 | 2025-05-05 | Not Started | No
TSK039 | Document Requirements | New Feature Dev | George | 2025-04-08 | 2025-04-22 | In Progress | No
TSK040 | Design UI/UX | New Feature Dev | Hannah | 2025-04-23 | 2025-05-07 | Not Started | No
TSK041 | Develop Feature | New Feature Dev | Ian | 2025-05-08 | 2025-05-22 | Not Started | No
TSK042 | Create Test Cases | Quality Assurance | Julia | 2025-04-15 | 2025-04-29 | In Progress | No
TSK043 | Execute Tests | Quality Assurance | Kevin | 2025-04-30 | 2025-05-14 | Not Started | No
TSK044 | Report Bugs | Quality Assurance | Laura | 2025-05-15 | 2025-05-29 | Not Started | No
TSK045 | Update Documentation | Knowledge Base | Michael | 2025-04-01 | 2025-04-18 | In Progress | No
TSK046 | Review Articles | Knowledge Base | Nancy | 2025-04-19 | 2025-05-03 | Not Started | No
TSK047 | Publish Updates | Knowledge Base | Oliver | 2025-05-04 | 2025-05-18 | Not Started | No
TSK048 | Plan Next Sprint | Agile Development | Patricia | 2025-04-14 | 2025-04-17 | Completed | No
TSK049 | Conduct Daily Stand-up | Agile Development | Quinn | 2025-04-18 | 2025-04-25 | In Progress | No
TSK050 | Hold Sprint Review | Agile Development | Rachel | 2025-04-26 | 2025-04-29 | Not Started | No
Formulas:
Is Overdue? = IF(AND([Status]<>"Completed",[Due Date]<TODAY()),"Yes","No")